## Sheet1
T0-1 Orbit
T0
[6 empty] | Baseline | [7 empty] | SAA |  |  | additional observations every orbit
[8 empty] | SAA | [5 empty] | 6:03
4:20
5:21 05:52 ± 18 sec 6:04
|  |  |  | 3:45 |  |  | 4:28
PPST |  |  |  |  | 1. UVOT with UVW1 filter | [6 empty] | 1. UVOT with UVW1 filter
[5 empty] | 2. XRT in PC | [6 empty] | 2. XRT in PC
|  | UVOT blocked | [6 empty] | UVOT blocked | [6 empty] | UVOT blocked
|  | XRT in auto | [6 empty] | XRT in auto | [6 empty] | XRT in auto
TDRSS | [11 empty] | 1. TDRSS forward
ATS
No BAT Data Downloading
Malindi Pass |  |  | Malindi Pass | [5 empty] | Malindi Pass |  |  |  |  | Malindi Pass |  |  | Malindi Pass
Malindi Gap
23:41 |  |  | 3:06 | [5 empty] | 4:49 | 5:01 |  |  |  | 6:33 | 6:43 |  | 13:29
1. Disable ATs |  |  | 1. ICU TDRSS H/K | [13 empty] | 1. Re-enable ATs
2. Blocked PPTs |  |  | 2. DPU TDRSS H/K | [13 empty] | 2. UVOT blocking until Tues. 13:00
3. Change S.C. trip filter 5 cycles | [16 empty] | 3. XRT continues using PC mode for comet
4. PCT hold 13 | [16 empty] | 4. Change S.C. trip filter back to default (TBS sec)
5. Turn off DPU & ICU TDRSS H/K
6. Upload ToO if needed to change UCOT mode
7. Reset Instument Parameters
8. PCT hold 12
Comet Tempel Team
| MOC Control Room | [6 empty] | Instrument & Data Support
| Principle Investigator: |  |  | Neil Gehrels (GSFC) - on call |  |  |  | UVOT Duty Specialist #1 (DPU): |  |  |  | Scott Koch
| Science Director: |  |  | Alan Wells |  |  |  | UVOT Data Analyst: |  |  |  | Nino Cucchiara
| UVOT Science Lead: |  |  | Keith Mason |  |  |  | UVOT Analysis Support: |  |  |  | Alex Blustin
| Obs. Duty Scientist: |  |  | Pete Roming | [7 empty] | Katie McGowan
| Flight Ops. #1: |  |  | Mark Hilliard |  |  |  | XRT Duty Scientist: |  |  |  | Dave Burrows
| Flight Ops. #2: |  |  | Rob Laverghetta |  |  |  | XRT Data Analyst: |  |  |  | Paul O'Bryan (UL)
| Flight Ops. Support: |  |  | Chris Bessette |  |  |  | XRT Analysis Support: |  |  |  | Cheryl Hurkett
| Science Planner #1: |  |  | Sally Hunsberger |  |  |  | XRT Pass One Support: |  |  |  | Judy Racusin
| UVOT Specialist #2 (ICU): |  |  | Phil Smith (MSSL) |  |  |  | XRT Analysis Support: |  |  |  | Dirk Grupe
| Coordination: |  |  | Marg Chester |  |  |  | BAT Duty Scientist: |  |  |  | Scott Barthelmy (GSFC)
[8 empty] | SDC Duty Scientists: |  |  |  | Richard Fink
Dean Hinshaw
[8 empty] | Science Planner #2: |  |  |  | Judy Racusin
[8 empty] | Systems Support: |  |  |  | Dale Hoover
[8 empty] | Web Support: |  |  |  | Meghan Clutter
[8 empty] | Publicity: |  |  |  | Barbara Kennedy
Martin de la Nougerede
Lynn Cominsky
Chris Wanjek
Tempel Schedule